## stories
Personal Finance Software
Date - 16/02/21
Initial_Tasks (#1)
Name | Subtasks | Status | Story Type | Due Date
UML Diagram of our software |  | To do | Chore | 2021-02-23
ER DIagram of our software |  | To do | Chore | 2021-02-23
Finalizing the modules of our project |  | To do | Chore | 2021-02-23
Creating an environment for development of backend in Django |  | To do | Chore | 2021-02-23
Working on finalizing the front-end for login and dashboard pages |  | To do | Feature | 2021-02-23
Creating the database structure |  | To do | Feature | 2021-02-23
Exploring more about the fundamentals of ScrumBan |  | To do | Chore | 2021-02-23
Visualizing the basic flow of our Project |  | To do | Chore | 2021-02-23
Making a use-case diagram for our software |  | To do | Chore | 2021-02-23
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah