## stories
Personal Finance Software
Date - 23/02/21 |  |  |  |  | The due date is a little high due to the mid-semester exams in that week
Tasks (#2)
Name | Subtasks | Status | Story Type | Due Date
UML diagram |  | Working on it | Chore | 2021-03-07
E-R diagrams - Physical & Logical |  | Ready for review | Chore | 2021-03-07
Creating an Environment for development of backend in django |  | Done | Feature | 2021-03-07
The front-end of login page |  | Ready for development | Feature | 2021-03-07
The front-end of dashboard page |  | Ready for development | Feature | 2021-03-07
Creating the database structure from the E-R diagram |  | Working on it | Feature | 2021-03-07
Visualizing and finalizing the flow of the project |  | Done | Chore | 2021-03-07
The Use-Case diagram of the software |  | Working on it | Chore | 2021-03-07
Making the Data Flow Diagram (Level 0,1,2) |  | To do | Chore | 2021-03-07
Making the Sequence Diagram |  | To do | Chore | 2021-03-07
Making the SRS (System Requirement Specification) Document |  | To do | Chore | 2021-03-07
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah