## stories
Personal Finance Software
Date - 07/03/21
Tasks (#3)
Name | Subtasks | Status | Story Type | Due Date
Front-end for the add expense page |  | To do | Feature | 2021-03-14
Front-end for the add iincome page |  | To do | Feature | 2021-03-14
Back-end for the add income page |  | To do | Feature | 2021-03-14
Back-end for the add expense page |  | To do | Feature | 2021-03-14
Connecting the add income page to the database |  | To do | Chore | 2021-03-14
Connecting the add expense page to the database |  | To do | Chore | 2021-03-14
Finalizing the dashboard's backend - includes charts, graphs, etc. |  | Ready for development | Chore | 2021-03-14
The front-end of login page |  | Working on it | Feature | 2021-03-14
The front-end of dashboard page |  | Working on it | Feature | 2021-03-14
Making the Data Flow Diagram Level 1 and Level 2 |  | Working on it | Chore | 2021-03-14
Sequence Diagram |  | Working on it | Chore | 2021-03-14
Making the SRS (System Requirement Specification) document |  | Working on it | Chore | 2021-03-14
The back-end connection for login page |  | Working on it | Feature | 2021-03-14
Data Flow Diagram level 0 |  | Ready for review | Chore | 2021-03-14
UML diagram |  | Ready for review | Chore | 2021-03-14
Use Case diagram |  | Ready for review | Chore | 2021-03-14
Compelte database structure created in postgresql |  | Done | Chore | 2021-03-14
Solved the errors faced in connecting the database |  | Done | Chore | 2021-03-14
E-R Diagrams Physical and Logical |  | Done | Chore | 2021-03-14
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah