## stories
Personal Finance Software
Date - 14/03/21
Tasks(#4)
Name | Subtasks | Status | Story Type | Due Date
Working on developing the dashboard |  | To do | Feature | 2021-03-21
Writing the code for the charts/graphs to be shown in the database |  | To do | Feature | 2021-03-21
Making the state diagram of the project |  | To do | Chore | 2021-03-21
Working on solving the errors in backend of add income page |  | To do | Bug | 2021-03-21
Improving the SRS (System Requirement Specification) document |  | To do | Chore | 2021-03-21
Back-end of add expense page |  | Ready for development | Feature | 2021-03-21
Connecting the add income page to the database |  | Ready for development | Chore | 2021-03-21
Connecting the add expense page to the database |  | Ready for development | Chore | 2021-03-21
Data Flow Diagram level 2 |  | Working on it | Chore | 2021-03-21
The back-end connection for dashboard page |  | Working on it | Feature | 2021-03-21
Front-end of add income page |  | Working on it | Feature | 2021-03-21
Front-end of add expense page |  | Working on it | Feature | 2021-03-21
Backend of add income page |  | Working on it | Feature | 2021-03-21
SRS (System Requirement Specification) Document |  | Working on it | Chore | 2021-03-21
The front-end of login page |  | Ready for review | Feature | 2021-03-21
The front-end of dashboard page |  | Ready for review | Feature | 2021-03-21
Data Flow Diagram level 1 |  | Ready for review | Chore | 2021-03-21
Sequence Diagram |  | Ready for review | Chore | 2021-03-21
The back-end connection for login page |  | Ready for review | Feature | 2021-03-21
UML Diagram |  | Done | Chore | 2021-03-21
Use Case Diagram |  | Done | Chore | 2021-03-21
Data flow diagram level 0 |  | Done | Chore | 2021-03-21
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah