## stories
Personal Finance Software
Date - 21/03/21
Tasks(#5)
Name | Subtasks | Status | Story Type | Due Date
The front-end of add goals page |  | To do | Feature | 2021-03-28
The backend of add goals page |  | To do | Feature | 2021-03-28
The frontend of view goals page |  | To do | Feature | 2021-03-28
The backend of view goals page |  | To do | Feature | 2021-03-28
Connecting the backend of the goals page with the database |  | To do | Chore | 2021-03-28
Working on making the user activity diagrams |  | To do | Chore | 2021-03-28
Back-end of add expense page |  | Working on it | Feature | 2021-03-28
Working on the backend connections of dashboard |  | Working on it | Chore | 2021-03-28
Connecting the code for graphs/charts with the backend database |  | Working on it | Chore | 2021-03-28
State diagram of the project |  | Working on it | Chore | 2021-03-28
Working on solving the errors in the backend of income page |  | Working on it | Bug | 2021-03-28
Data flow diagram level 2 |  | Ready for review | Chore | 2021-03-28
The back-end connection for dashboard page |  | Ready for review | Feature | 2021-03-28
Front-end of add income page |  | Ready for review | Feature | 2021-03-28
Front-end of add expense page |  | Ready for review | Feature | 2021-03-28
Backend of add income page |  | Ready for review | Feature | 2021-03-28
SRS (System Requirement Specification) document |  | Ready for review | Chore | 2021-03-28
The frontend of login page |  | Done | Feature | 2021-03-28
The frontend of dashboard page |  | Done | Feature | 2021-03-28
Data flow diagram level 1 |  | Done | Chore | 2021-03-28
Sequence diagram |  | Done | Chore | 2021-03-28
The back-end connection for login page |  | Done | Chore | 2021-03-28
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah