## stories
Personal Finance Software
Date - 28/03/21
Tasks(#6)
Name | Subtasks | Status | Story Type | Due Date
developing the dynamic buttons for the add goals page |  | To do | Feature | 2021-04-04
developing the dynamic buttons for the delete goals page |  | To do | Feature | 2021-04-04
working on the code for making the weekly and monthly line charts of income and expenses |  | To do | Feature | 2021-04-04
working on creating the design document |  | To do | Chore | 2021-04-04
Working on mobile phone and email validation for the sign up page |  | To do | Feature | 2021-04-04
connecting the backend of the goals page with the database |  | Ready for development | Chore | 2021-04-04
front-end of add goals page |  | Working on it | Feature | 2021-04-04
Backend of add goals page |  | Working on it | Feature | 2021-04-04
frontend of view goals page |  | Working on it | Feature | 2021-04-04
backend of view goals page |  | Working on it | Feature | 2021-04-04
making the user activity diagrams |  | Working on it | Chore | 2021-04-04
Working on solving some errors in connecting backend of goals page to database |  | Working on it | Bug | 2021-04-04
Back-end of add expense page |  | Ready for review | Feature | 2021-04-04
Connecting the codes of graph/charts with the database |  | Ready for review | Chore | 2021-04-04
State diagram of the project |  | Ready for review | Chore | 2021-04-04
The errors of the add income page solved |  | Ready for review | Bug | 2021-04-04
Data flow diagram level 2 |  | Done | Chore | 2021-04-04
The back-end connection for dashboard page |  | Done | Chore | 2021-04-04
Front-end of add income page |  | Done | Feature | 2021-04-04
Front-end of add expense page |  | Done | Feature | 2021-04-04
Back-end of add income page |  | Done | Feature | 2021-04-04
SRS (system Requirement specification) document |  | Done | Chore | 2021-04-04
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah