## stories
Personal Finance Software
Date - 04/04/21
Tasks(#7)
Name | Subtasks | Status | Story Type | Due Date
A little editing in the System Requirement Specification document |  | To do | Chore | 2021-04-11
Front-end of view bills page |  | To do | Feature | 2021-04-11
Back-end of view bills page |  | To do | Feature | 2021-04-11
Making small changes in the Data flow diagram |  | To do | Chore | 2021-04-11
Reviewing the methodologies for testing our project |  | To do | Chore | 2021-04-11
Establishing a connection from the view bills page to the database |  | Ready for development | Chore | 2021-04-11
Developing the dynamic buttons for add goals page |  | Working on it | Feature | 2021-04-11
Working on code for making the weekly and monthly line charts of income and expenses |  | Working on it | Chore | 2021-04-11
Working on mobile phone and email validation for the sign up page |  | Working on it | Feature | 2021-04-11
Back-end of view goals page |  | Working on it | Feature | 2021-04-11
Front-end of add goals page |  | Ready for review | Feature | 2021-04-11
Back-end of add goals page |  | Ready for review | Feature | 2021-04-11
Front-end of view goals page |  | Ready for review | Feature | 2021-04-11
The user activity diagrams |  | Ready for review | Chore | 2021-04-11
Checking the errors in the back-end of goals page connection to database |  | Ready for review | Bug | 2021-04-11
The design Document |  | Done | Chore | 2021-04-11
The errors of the add income page solved |  | Done | Bug | 2021-04-11
State diagram of the project |  | Done | Chore | 2021-04-11
back-end of add expense page |  | Done | Feature | 2021-04-11
Connecting the codes of graphs/ charts with the database |  | Done | Chore | 2021-04-11
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah