## stories
Personal Finance Software
Date - 11/04/21
Tasks(#8)
Name | Subtasks | Status | Story Type | Due Date
Front-end of add goals page |  | Done | Feature | 2021-04-20
Back-end of add goals page |  | Done | Feature | 2021-04-20
Solving the errors for making the pie-charts dynamic |  | To do | Bug | 2021-04-20
Front-end of view goals page |  | Done | Feature | 2021-04-20
The user activity diagrams |  | Done | Chore | 2021-04-20
Checking the errors in the back-end of the goals page connection to database |  | Done | Bug | 2021-04-20
back-end of view goals page |  | Ready for review | Feature | 2021-04-20
Developing the dynamic buttons for add goals page |  | Ready for review | Feature | 2021-04-20
Developing the dynamic buttons for view goals page |  | To do | Feature | 2021-04-20
The code for making the weekly and monthly line charts of income and expenses |  | Ready for review | Feature | 2021-04-20
Mobile phone and email validation for the sign up page |  | Ready for review | Feature | 2021-04-20
Non-negative income validation for the add income page |  | To do | Feature | 2021-04-20
Non-negative expense validation for the add expense page |  | To do | Feature | 2021-04-20
Front-end of view bills page |  | Working on it | Feature | 2021-04-20
back-end of view bills page |  | Working on it | Feature | 2021-04-20
Establishing a connection from the view bills page to the database |  | Working on it | Chore | 2021-04-20
Making small changes in the DFD level 2 |  | Working on it | Chore | 2021-04-20
Reviewing testing methodologies for testing our project |  | Working on it | Chore | 2021-04-20
Solving some errors faced in front-end alignment of buttons on add goals page |  | To do | Bug | 2021-04-20
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah