## stories
Personal Finance Software
Date - 20/04/21
Tasks(#9)
Name | Subtasks | Status | Story Type | Due Date
back-end of view goals page |  | Done | Feature | 2021-05-03
The code for making the weekly and monthly line charts for income and expenses |  | Done | Feature | 2021-05-03
Mobile phone and email validation for the sign up page |  | Done | Feature | 2021-05-03
front-end of view bills page |  | Ready for review | Feature | 2021-05-03
back-end of view bills page |  | Ready for review | Feature | 2021-05-03
Establishing a connection from the view bills page to the database |  | Ready for review | Chore | 2021-05-03
Small changes in the Data flow Diagram level 2 |  | Ready for review | Chore | 2021-05-03
Testing methodologies to test our project |  | Ready for review | Chore | 2021-05-03
Developing the dynamic buttons for view goals page |  | Working on it | Feature | 2021-05-03
Non-negative income validation for the add income page |  | Working on it | Chore | 2021-05-03
Non-negative expense validation for the add expense page |  | Working on it | Chore | 2021-05-03
Solving the errors for making the pie chart dynamic |  | Working on it | Bug | 2021-05-03
Developing the dynamic buttons for add goals page |  | Working on it | Feature | 2021-05-03
Work on creating a dynamic progress bar for every goal |  | To do | Feature | 2021-05-03
Solving some errors faced in front-end alignment of buttons on Add goals page |  | To do | Bug | 2021-05-03
Start working on preparing the coding document of the project |  | To do | Chore | 2021-05-03
Doing final code checks for modules that are properly working |  | To do | Chore | 2021-05-03
TEAM MEMBERS
Vidit Vaywala
Hemil Shah
Varshil Shah
Meet Kadiya
Yash Arvindkumar Patel
Kahaan Patel
Sharvil Patel
Priyanshi Shah